## Start Here
Indie Film Production System · Budget & Planning Workbook
Companion to the printable Indie Film Production System
HOW TO USE
1. Project | Fill in your project details below.
2. Budget | Enter quantity, unit, and rate for each line. Totals, subtotals, contingency, and the grand total calculate automatically.
3. Top Sheet | Summarizes every category. Actual spending pulls in automatically from the Expenses tab.
4. Scene Breakdown | List every scene. Enter pages as whole pages plus eighths. Total pages feed the shoot day estimate.
5. Schedule | One row per scene with setup and shoot time estimates. Summary totals for pages, hours, moves, and scenes remaining are at the bottom.
6. Cast & Crew | Enter day rates and days. Labor totals calculate automatically.
7. Expenses | Log every purchase and pick a category from the dropdown. Actuals flow to the Top Sheet.
8. Funding | Track every dollar raised against your grand total.
9. Day Out of Days | Mark W (work), H (hold), T (travel) for each actor. Work days count automatically.
10. Availability | Actor and Location Availability matrices show the best days to shoot.
COLOR KEY
Blue text, yellow cell | Your inputs. Type here.
Black text | Formulas. Don't type over these.
Orange cell | Key totals.
PROJECT
Title | Example: Last Light on Fulton Street
Production company
Director
Producer
Format | Feature
Budget tier | Ultra Low
Shoot start date
Target runtime (min) | 90
Note | Example entries are shown in each tab's first row. Replace them with your own. This workbook is a planning tool, not legal or financial advice.

## Top Sheet
Budget Top Sheet
Budget pulls from the Budget tab. Actual pulls from the Expenses tab. Nothing to type here.
Section | Category | Budget ($) | Actual ($) | Remaining ($) | % spent
ATL | Story, rights & writer | 1500 | 0 | 1500 | 0%
ATL | Producers | 0 | 0 | 0 | 0%
ATL | Director | 0 | 0 | 0 | 0%
ATL | Cast | 0 | 0 | 0 | 0%
BTL | Production staff | 0 | 0 | 0 | 0%
BTL | Camera | 850 | 850 | 0 | 100%
BTL | Grip & electric | 0 | 0 | 0 | 0%
BTL | Sound | 0 | 0 | 0 | 0%
BTL | Art, props & set dressing | 0 | 0 | 0 | 0%
BTL | Wardrobe, hair & makeup | 0 | 0 | 0 | 0%
BTL | Locations & permits | 0 | 0 | 0 | 0%
BTL | Transportation & travel | 0 | 0 | 0 | 0%
BTL | Catering & craft services | 0 | 0 | 0 | 0%
Post | Editing | 0 | 0 | 0 | 0%
Post | Sound design, music & mix | 0 | 0 | 0 | 0%
Post | Color, VFX & titles | 0 | 0 | 0 | 0%
Other | Insurance & legal | 0 | 0 | 0 | 0%
Other | Festivals, marketing & deliverables | 0 | 0 | 0 | 0%
| SUBTOTAL | 2350 | 850 | 1500
| CONTINGENCY | 235
| GRAND TOTAL | 2585 | 850 | 1735
ATL = above the line (creative leads). BTL = below the line (crew and production). Green = pulled from another tab.

## Budget
Detailed Budget
Enter Qty × Rate for each line. Subtotals, contingency, and grand total calculate automatically.
Line item | Qty | Unit | Rate ($) | Total ($) | Notes
STORY, RIGHTS & WRITER
Script purchase / option |  |  |  | 0
Writer fee | 1 | Flat | 1500 | 1500 | Example: writer fee. Replace with your numbers.
Rewrites |  |  |  | 0
Subtotal: Story, rights & writer |  |  |  | 1500
PRODUCERS
Producer fee |  |  |  | 0
Line producer / UPM |  |  |  | 0
Subtotal: Producers |  |  |  | 0
DIRECTOR
Director fee |  |  |  | 0
Subtotal: Director |  |  |  | 0
CAST
Lead cast |  |  |  | 0
Supporting cast |  |  |  | 0
Day players |  |  |  | 0
Background actors |  |  |  | 0
Casting costs |  |  |  | 0
Union fringes / payroll fees |  |  |  | 0
Subtotal: Cast |  |  |  | 0
PRODUCTION STAFF
1st AD |  |  |  | 0
Production coordinator |  |  |  | 0
Production assistants |  |  |  | 0
Script supervisor |  |  |  | 0
Subtotal: Production staff |  |  |  | 0
CAMERA
Director of photography |  |  |  | 0
1st AC / camera operator |  |  |  | 0
Camera package rental | 1 | Weeks | 850 | 850 | Example: weekly package rate from a rental house.
Lenses |  |  |  | 0
Media and hard drives |  |  |  | 0
Subtotal: Camera |  |  |  | 850
GRIP & ELECTRIC
Gaffer |  |  |  | 0
Key grip |  |  |  | 0
Lighting package |  |  |  | 0
Grip package |  |  |  | 0
Generator / power |  |  |  | 0
Subtotal: Grip & electric |  |  |  | 0
SOUND
Sound mixer |  |  |  | 0
Boom operator |  |  |  | 0
Sound package |  |  |  | 0
Expendables and batteries |  |  |  | 0
Subtotal: Sound |  |  |  | 0
ART, PROPS & SET DRESSING
Production designer |  |  |  | 0
Props |  |  |  | 0
Set dressing |  |  |  | 0
Art supplies |  |  |  | 0
Subtotal: Art, props & set dressing |  |  |  | 0
WARDROBE, HAIR & MAKEUP
Wardrobe purchases |  |  |  | 0
Hair and makeup artist |  |  |  | 0
Makeup supplies |  |  |  | 0
Subtotal: Wardrobe, hair & makeup |  |  |  | 0
LOCATIONS & PERMITS
Location fees |  |  |  | 0
Permits |  |  |  | 0
Location insurance certificates |  |  |  | 0
Cleaning and repairs |  |  |  | 0
Subtotal: Locations & permits |  |  |  | 0
TRANSPORTATION & TRAVEL
Vehicle rental |  |  |  | 0
Gas and mileage |  |  |  | 0
Lodging |  |  |  | 0
Parking |  |  |  | 0
Subtotal: Transportation & travel |  |  |  | 0
CATERING & CRAFT SERVICES
Meals |  |  |  | 0
Craft services |  |  |  | 0
Water and coffee |  |  |  | 0
Subtotal: Catering & craft services |  |  |  | 0
EDITING
Editor |  |  |  | 0
Assistant editor |  |  |  | 0
Edit system / storage |  |  |  | 0
Subtotal: Editing |  |  |  | 0
SOUND DESIGN, MUSIC & MIX
Sound design / dialogue edit |  |  |  | 0
Final mix |  |  |  | 0
Composer |  |  |  | 0
Music licensing |  |  |  | 0
Subtotal: Sound design, music & mix |  |  |  | 0
COLOR, VFX & TITLES
Color grade |  |  |  | 0
VFX |  |  |  | 0
Titles and graphics |  |  |  | 0
Captions / subtitles |  |  |  | 0
Subtotal: Color, VFX & titles |  |  |  | 0
INSURANCE & LEGAL
General liability insurance |  |  |  | 0
Equipment insurance |  |  |  | 0
E&O insurance |  |  |  | 0
Legal fees |  |  |  | 0
Company / LLC fees |  |  |  | 0
Subtotal: Insurance & legal |  |  |  | 0
FESTIVALS, MARKETING & DELIVERABLES
Festival submissions |  |  |  | 0
Poster and key art |  |  |  | 0
Trailer |  |  |  | 0
Deliverables / QC |  |  |  | 0
Marketing and ads |  |  |  | 0
Subtotal: Festivals, marketing & deliverables |  |  |  | 0
SUBTOTAL, ALL CATEGORIES |  |  |  | 2350
Contingency % |  |  | 10% | 235 | Industry rule of thumb is about 10%. Adjust to your comfort level.
GRAND TOTAL |  |  |  | 2585

## Expenses
Expense Log
Log every purchase. Pick a category so actual spending flows to the Top Sheet.
Category list
Date | Vendor | Description | Category | Amount ($) | Paid by | Receipt? | Story, rights & writer
2026-10-03 | Local rental house | Example: camera package, 1 week | Camera | 850 | Producer | Yes | Producers
Director
Cast
Production staff
Camera
Grip & electric
Sound
Art, props & set dressing
Wardrobe, hair & makeup
Locations & permits
Transportation & travel
Catering & craft services
Editing
Sound design, music & mix
Color, VFX & titles
Insurance & legal
Festivals, marketing & deliverables
|  |  | TOTAL SPENT | 850

## Scene Breakdown
Scene Breakdown
One row per scene. Pages = whole pages + eighths (e.g., 1 and 3 = 1 3/8 pages).
Scene # | INT/EXT | Day/Night | Location / set | Description | Whole pages | Eighths (0-7) | Page count | Cast IDs | Props / wardrobe | Special needs | Shoot day
1 | INT | DAY | Maya's apartment · kitchen | Example: Maya finds the letter on the counter | 1 | 3 | 1.375 | 1, 2 | Letter, coffee mug | None | 1
|  |  |  | TOTAL PAGES |  |  | 1.375
|  |  |  | Scenes listed |  |  | 1
|  |  |  | Target pages per shoot day |  |  | 5 | Many microbudget features plan roughly 3 to 6 pages a day.
|  |  |  | Buffer days % |  |  | 10%
|  |  |  | ESTIMATED SHOOT DAYS |  |  | 1

## Schedule
Master Shooting Schedule
One row per scene. Number shoot days 1, 2, 3... Setup and shoot times are in minutes; total hours calculate automatically.
Day | Date | Scene | Location | Cast IDs | Pages | Day / Night | Est. setup (min) | Est. shoot (min) | Total hours | Company move? | Meal | Status | Notes
1 | 2026-10-10 | 1 | Maya's apartment · kitchen | 1, 2 | 1.375 | DAY | 45 | 90 | 2.25 | No | Before | Scheduled | Example row. Kitchen first while the light is right
|  |  | TOTAL PAGES |  |  | 1.375
|  |  | Shoot days (highest day number) |  |  | 1
|  |  | Avg pages / day |  |  | 1.375
|  |  | Total estimated hours |  |  | 2.25
|  |  | Avg hours / day |  |  | 2.25
|  |  | Company moves |  |  | 0
|  |  | Scenes shot |  |  | 0
|  |  | Scenes remaining |  |  | 1
Hours for one day: use the Total hours column, or filter by Day. Keep shoot days near 12 hours or less, including meals, and allow proper rest between days.

## Cast & Crew
Cast & Crew
Contacts, rates, and labor cost. Total = day rate × days + flat fees.
ID | Name | Role / position | Dept | Phone | Email | Day rate ($) | Days | Flat fees ($) | Total ($) | Deal memo signed?
1 | Jordan Ellis | Maya (lead) | Cast | 555-0100 | jordan@email.com | 250 | 12 | 0 | 3000 | Yes
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
[8 empty] | TOTAL LABOR | 3000

## Locations
Locations & Permits
Every place you'll shoot, cleared and confirmed.
Location | Address | Scenes | Contact | Phone | Shoot dates | Fee ($) | Release signed? | Permit needed? | Permit # | Notes
Maya's apartment | 123 Example Ave | 1, 4, 9 | Owner name | 555-0101 | Oct 10-11 | 300 | Yes | No |  | Example row. Quiet after 9 AM
[5 empty] | TOTAL FEES | 300

## Funding
Funding Tracker
Every dollar raised, compared with your grand total.
Source | Type | Committed ($) | Received ($) | Date received | Terms / notes
Example: Kickstarter | Crowdfunding | 8000 | 7200 | 2026-09-01 | Rewards: digital download, credits
| Total committed | 8000
| Total received | 7200
| Budget grand total | 2585
| STILL NEEDED | 0
| % funded (committed) | 309.5%

## Day Out of Days
Day Out of Days
W = work, S = start, F = finish, H = hold (paid, not working), T = travel. Counts calculate automatically.
Cast ID | Character | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | Work days | Hold days | Travel days
1 | Maya | D1: SW; D2: W; D3: W; D4: H; D5: WF | 4 | 1 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0
[32 empty] | 0 | 0 | 0

## Actor Availability
Actor Availability Matrix
Mark each actor for every shoot date. Build the schedule around the hardest calendars first.
Actor | Role / notes | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | Available | Booked
Shoot date →
Jordan Ellis (example) | Maya · lead | D1: Y; D2: Y; D3: N; D4: Y; D5: B | 3 | 1
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
Not available that day |  | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Codes: Y = available, N = not available, ? = maybe, B = booked. Enter shoot dates in row 6. The bottom row shows how many are unavailable each day, so the best days have the lowest number.

## Location Availability
Location Availability Matrix
Mark each location for every shoot date. Compare with Actor Availability to find your best days.
Location | Role / notes | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28 | D29 | D30 | Available | Booked
Shoot date →
Maya's apartment (example) | Weekdays after 9 AM | D1: Y; D2: Y; D3: Y; D4: N; D5: B | 3 | 1
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
[32 empty] | 0 | 0
Not available that day |  | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Codes: Y = available, N = not available, ? = maybe, B = booked. Enter shoot dates in row 6. The bottom row shows how many are unavailable each day, so the best days have the lowest number.